## Blank Pay Application
AIA-Style Pay Application (similar to AIA G702)
Attach with Continuation Sheet (similar to AIA G703) for each billing period Disclaimer: This Schedule of Values template is provided for demonstration and general project management use only. It is not an official AIA® G703 form and does not reproduce any copyrighted AIA® material. This version assumes a fixed retainage rate (for example, 10%) applied uniformly to all line items. It does not account for partial retainage release, variable rates, or special retainage agreements. You can modify the retainage line by item or period if you're using variable retainage
To Owner:
From Contractor:
Project:
Project No:
Application No.
Contract For:
Contract Date: | 00/00/0000
Period To: | 00/00/0000
Date of Application: | 00/00/0000
CONTRACTOR'S APPLICATION FOR PAYMENT
1. Original Contract Amount: | 0
2. Approved Change Orders (Net): | 0
3. Adjusted Contract Amount (1 + 2): | 0
4. Total Completed & Stored to Date (from Schedule of Values): | 0
5. Retainage (fixed amount entered by user): | 0
6. Total Earned Less Retainage (4 - 5): | 0
7. Less Previous Certificates for Payment: | 0
8. Current Payment Due (6 - 7): | 0
9. Balance to Finish, Including Retainage (3 - 4): | 0
ARCHITECT'S CERTIFICATE FOR PAYMENT
Leave this area blank for the architect or owner’s representative to complete after reviewing the application. It confirms that the listed work and amounts are approved for payment.
Approved by (Architect/owner etc.)
Date: | 00/00/0000
Amount Certified: | 0
Signature:
Printed Name:
Title:
Explore how BQE software can streamline your billing and speed up your cash flow.

## Example Pay Application
AIA-Style Pay Application (similar to AIA G702)
Attach with Continuation Sheet (similar to AIA G703) for each billing period Disclaimer: This Schedule of Values template is provided for demonstration and general project management use only. It is not an official AIA® G703 form and does not reproduce any copyrighted AIA® material. This version assumes a fixed retainage rate (for example, 10%) applied uniformly to all line items. It does not account for partial retainage release, variable rates, or special retainage agreements. You can modify the retainage line by item or period if you're using variable retainage
To Owner: | Main Street Development Group |  | << The legal name of the project owner or client who will receive the application and issue payment
From Contractor: | Urban Builders LLC |  | << Write the full legal name of the contractor or firm submitting the payment request.
Project: | State Street Office Renovation |  | << Type the official project name as shown on the project documents
Project No: | 45962 |  | << Enter the project or contract identification number assigned by the owner or architect.
Application No. | 3 |  | << Indicate the sequential number of this pay application (e.g., 1, 2, 3).
Contract For: | Office improvement |  | << Describe the scope of work or contract title.
Contract Date: | 2025-03-30 |  | << Date that contract was complete.
Period To: | 2025-11-30 |  | << Write the last date covered by this billing period.
Date of Application: | 2025-11-30 |  | << Date this application is prepared and submitted
CONTRACTOR'S APPLICATION FOR PAYMENT
1. Original Contract Amount: | 100000 | << Found in the signed contract (AIA A101 or similar)
2. Approved Change Orders (Net): | 10000 | << From approved Change order logs (usually on project C tracker or AIA G701)
3. Adjusted Contract Amount (1 + 2): | 110000 | << Calculated directly on G702
4. Total Completed & Stored to Date (from Schedule of Values): | 85000 | << From G703 Column G ("total to date")
5. Retainage (fixed amount entered by user): | 8500 | << Calculated as per contract terms; usually 5-10% of line 4, unless partial releases are approved. You can modify the retainage line by item or period if you're using variable retainage
6. Total Earned Less Retainage (4 - 5): | 76500 | << Calculated as net earned amount after subtracting retainage
7. Less Previous Certificates for Payment: | 54000 | << Found in previous G702 (line 6) as the sum of the prior months' G702s
8. Current Payment Due (6 - 7): | 22500 | << Calculated on G702. Sum of the new work + stored materials - retainage
9. Balance to Finish, Including Retainage (3 - 4): | 33500 | << Remaining uncompleted portion of the adjusted contract. It still includes any retainage not yet released.
ARCHITECT'S CERTIFICATE FOR PAYMENT
Leave this area blank for the architect or owner’s representative to complete after reviewing the application. It confirms that the listed work and amounts are approved for payment.
Approved by (Architect/owner etc.)
Date: | 00/00/0000 |  | << Date of approval.
Amount Certified: | 0 |  | << The total dollar amount the architect or owner approves for payment on this application — may differ from the contractor’s requested amount if adjustments are made.
Signature: |  |  | << Signature of the architect or authorized representative certifying the payment.
Printed Name: |  |  | << Printed name of the architect or authorized representative certifying the payment.
Title: |  |  | << Title of the architect or authorized representative certifying the payment.
Explore how BQE software can streamline your billing and speed up your cash flow.

## Mid-payment Example
AIA-Style Pay Application (Summary)
To Owner: | Main Street Development Group
From Contractor: | Urban Builders LLC
Project: | State Street Office Renovation
Project No: | 2025-11-01
Application No. | 3
Period To: | 2025-11-30
Contract For: | Office improvement
Contract Date: | 2025-03-30
Date of Application: | 2025-11-30
1. Original Contract Amount | 100000
2. Approved Change Orders (Net) | 10000
3. Adjusted Contract Amount (1 + 2) | 110000
4. Total Completed & Stored to Date (from Schedule of Values) | 85000
5. Retainage (10%) | 8500
6. Total Earned Less Retainage (4 - 5) | 76500
7. Less Previous Certificates for Payment | 54000
8. Current Payment Due (6 - 7) | 22500
9. Balance to Finish, Including Retainage (3 - 6) | 33500
ARCHITECT'S CERTIFICATE FOR PAYMENT
Amount certified
Approved by (Architect/owner etc)

## End of Project Example
AIA-Style Pay Application (Summary)
To Owner: | Main Street Development Group
From Contractor: | Urban Builders LLC
Project: | State Street Office Renovation
Project No: | 2025-11-01
Application No. | 3
Period To: | 2025-11-30
Contract For: | Office improvement
Contract Date: | 2025-03-30
Date of Application: | 2025-11-30
1. Original Contract Amount | 100000
2. Approved Change Orders (Net) | 10000
3. Adjusted Contract Amount (1 + 2) | 110000
4. Total Completed & Stored to Date (from Schedule of Values) | 110000
5. Retainage (10%) | 0 | **assuming retainage is released on the final pay app
6. Total Earned Less Retainage (4 - 5) | 110000
7. Less Previous Certificates for Payment | 76500
8. Current Payment Due (6 - 7) | 33500
9. Balance to Finish, Including Retainage (3 - 6) | 0
ARCHITECT'S CERTIFICATE FOR PAYMENT
Amount certified
Approved by (Architect/owner etc)

## About BQE Core
Simplify your billing process with BQE CORE. Create invoices directly from your time and expense data, customize by project phase, and send dozens of invoices at once with batch billing. Plus built-in e-payments help you get paid faster and improve cash flow. Learn more: https://www.bqe.com/core-invoicing
You didn’t start your firm to chase timesheets, juggle spreadsheets, or guess at profitability. You did it to make an impact through great design, strong leadership, and a thriving team. That’s why we built BQE CORE, the all-in-one firm management software created by architects and engineers to simplify how A&E firms run. From time tracking to billing, project management to accounting, CORE brings it all together in one intuitive platform. Join the thousands of firms using CORE to save time, increase profitability, and get back to the work that matters. Book a demo to see how CORE can help your firm run smarter. <BOOK A DEMO>