## Blank Pay Continuation
AIA-Style Pay Continuation (Schedule of Values, similar to G703)
Attached to and forming part of the Payment Application (similar to AIA G702). Disclaimer: This Schedule of Values template is provided for demonstration and general project management use only. It is not an official AIA® G703 form and does not reproduce any copyrighted AIA® material. This version assumes a fixed retainage rate (for example, 10%) applied uniformly to all line items. It does not account for partial retainage release, variable rates, or special retainage agreements. Calculated as per contract terms; usually 5-10% of line 4, unless partial releases are approved. You can modify the retainage line by item or period if you're using variable retainage
Project Name: |  |  |  | Contractor:
Project Number: |  |  |  | Owner:
Application No: |  |  |  | Architect
Period To: | 00/00/0000
A. Item No. | B. Description of Work | C. Scheduled Value | D. Prior Work Billed | E. Work This Period | F. Materials Stored | G. Total to Date (D+E+F) | H. % Complete | I. Remaining Value | J. Retainage (10%)
1 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
2 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
3 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
4 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
5 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
6 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
7 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
8 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
9 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
10 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0
TOTALS |  | 0 | 0 | 0 | 0 | 0 | __ | 0 | 0
#VALUE! |  | Explore how BQE software can streamline your billing and speed up your cash flow.

## Example Pay Continuation
AIA-Style Pay Continuation (Schedule of Values, similar to G703)
Attached to and forming part of the Payment Application (similar to AIA G702). Disclaimer: This Schedule of Values template is provided for demonstration and general project management use only. It is not an official AIA® G703 form and does not reproduce any copyrighted AIA® material. This version assumes a fixed retainage rate (for example, 10%) applied uniformly to all line items. It does not account for partial retainage release, variable rates, or special retainage agreements. Calculated as per contract terms; usually 5-10% of line 4, unless partial releases are approved. You can modify the retainage line by item or period if you're using variable retainage
Project Name: | Full name or title of the project. Use the name on your contract |  |  |  | Contractor: | Name of the entity requesting payment - usually the contractor company name
Project Number: | Project number assigned on your contract |  |  |  | Owner: | The project owner or client’s legal name. Match it exactly as written on the contract.
Application No: | The sequential pay application number (e.g., “1” for the first billing, “2” for the next, etc.). It should match the Application No. on the G702 summary sheet. |  |  |  | Architect | The architect or contract administrator responsible for reviewing and certifying the pay application.
Period To: | The last day of the billing period
A. Item No. | B. Description of Work | Scheduled Value | D. Prior Work Billed | E. Work This Period | F. Materials Stored | G. Total to Date (D+E+F) | H. % Complete | I. Remaining Value | J. Retainage (10%)
| The work breakdown or trade (e.g. Sitework, Framing, Finishes, CO #1). Matches the line items in your contract or schedule of values. | Contract amount allocated to each line item. The sum of this column should equal the Adjusted Contract Amount (Line 3 on G702). | Total value of work for each line item that you completed in all prior pay apps (excluding this one). | Value of new work performed during this billing period. | Cost of materials delivered but not yet installed (on site or approved warehouse). | Cumulative value of all completed work and stored materials. The sum of this column = G702 Line 4. | Percentage of each line item completed to date. (Column G % C * 100%) | Value of uncompleted work for each item. (Column C - G) | Portion of earned value being withheld, usually 5 to 10%. (Column G * retainage %) The sum of this column = G702 Line 5. | *You can modify the retainage line by item or period if you're using variable retainage
1 | Sitework | 15000 | 15000 | 0 | 0 | 15000 | 100% | 0 | 1500
2 | Framing | 25000 | 20000 | 5000 | 0 | 25000 | 100% | 0 | 2500
3 | Finishes | 60000 | 25000 | 10000 | 5000 | 40000 | 67% | 20000 | 4000
4 | CO #1 – Added Lighting | 10000 | 0 | 3000 | 2000 | 5000 | 50% | 5000 | 500
TOTALS |  | 110000 | 60000 | 18000 | 7000 | 85000 | __ | 25000 | 8500
Explore how BQE software can streamline your billing and speed up your cash flow.

## Mid-payment example
AIA-Style Pay Continuation (Schedule of Values)
Attached to and forming part of the Payment Application (similar to AIA G702)
Project Name: | State Street Office Renovation |  |  |  | Contractor: | Urban Builders LLC
Project Number: | 2025-11 |  |  |  | Owner: | Main Street Development Group
Application No: | 3 |  |  |  | Architect | Smith Design Studios
Period To: | 2025-11-30
A. Item No. | B. Description of Work | C. Scheduled Value | D. Prior Work Billed | E. Work This Period | F. Materials Stored | G. Total to Date (D+E+F) | H. % Complete | I. Remaining Value | J. Retainage (10%)
1 | Sitework | 15000 | 15000 | 0 | 0 | 15000 | 100% | 0 | 1500
2 | Framing | 25000 | 20000 | 5000 | 0 | 25000 | 100% | 0 | 2500
3 | Finishes | 60000 | 25000 | 10000 | 5000 | 40000 | 67% | 20000 | 4000
4 | CO #1 – Added Lighting | 10000 | 0 | 3000 | 2000 | 5000 | 50% | 5000 | 500
| TOTALS | 110000 | 60000 | 18000 | 7000 | 85000 |  | 25000 | 8500

## Final payment example
AIA-Style Pay Continuation (Schedule of Values)
Attached to and forming part of the Payment Application (similar to AIA G702)
Project Name: | State Street Office Renovation |  |  |  | Contractor: | Urban Builders LLC
Project Number: | 2025-11 |  |  |  | Owner: | Main Street Development Group
Application No: | 4 |  |  |  | Architect | Smith Design Studios
Period To: | November 30 2025
A. Item No. | B. Description of Work | Scheduled Value | D. Prior Work Billed | E. Work This Period | F. Materials Stored | G. Total to Date (D+E+F) | H. % Complete | I. Remaining Value | J. Retainage (10%)
1 | Sitework | 15000 | 15000 | 0 | 0 | 15000 | 100% | 0 | -
2 | Framing | 25000 | 25000 | 0 | 0 | 25000 | 100% | 0 | -
3 | Finishes | 60000 | 40000 | 20000 | 0 | 60000 | 100% | - | -
4 | CO #1 – Added Lighting | 10000 | 5000 | 5000 | 0 | 10000 | 100% | - | -
| TOTALS | 110000 | 85000 | 25000 | 0 | 110000 | - | - | -

## About BQE Core
Simplify your billing process with BQE CORE. Create invoices directly from your time and expense data, customize by project phase, and send dozens of invoices at once with batch billing. Plus built-in e-payments help you get paid faster and improve cash flow. Learn more: https://www.bqe.com/core-invoicing
You didn’t start your firm to chase timesheets, juggle spreadsheets, or guess at profitability. You did it to make an impact through great design, strong leadership, and a thriving team. That’s why we built BQE CORE, the all-in-one firm management software created by architects and engineers to simplify how A&E firms run. From time tracking to billing, project management to accounting, CORE brings it all together in one intuitive platform. Join the thousands of firms using CORE to save time, increase profitability, and get back to the work that matters. Book a demo to see how CORE can help your firm run smarter. <BOOK A DEMO>