## Blank Invoice
INSERT FIRM LOGO | Architectural Services Invoice (Milestone/Progress)
Firm Name: |  |  |  | Invoice Number:
Address: |  |  |  | Date Issued:
Phone / Email: |  |  |  | Payment Due Date:
License Number: |  |  |  | Project Number / Code:
FOR
Client Name:
Client Company:
Project Name:
Project Address:
Fees
Project Phase | Total Fee | % Complete | Amount This Invoice | Balance Remaining | Notes
| 0 | 0% | 0 | 0
| 0 | 0% | 0 | 0
| 0 | 0% | 0 | 0
| 0 | 0% | 0 | 0
| 0 | 0% | 0 | 0
| 0 | 0% | 0 | 0
Subtotals Fees | 0 | — | 0 | 0
Reimbursable Expenses
Description | Vendor Source |  | Amount | Notes
0
0
0
0
Subtotal Reimbursables |  |  | 0
Summary
|  |  | Percentage | Amount
Fees |  |  | __ | 0
Reimbursables |  |  | __ | 0
Markup (% and amount) |  |  | 0% | 0
Taxes (% and amount) |  |  | 0% | 0
Retainage (% and amount) |  |  | 0% | 0
Total Due This Invoice (labor + reimbursables + markup + tax - retainage) |  |  |  | 0
Payment Terms: (e.g., Net 30 days)
Accepted Payment Methods: (bank transfer, check, e-payment link)
E-payment Link:
Notes (e.g., “Final payment due upon substantial completion.”)
Explore how BQE software can automate your batch invoicing and other time-saving tools.

## Sample Invoice
INSERT FIRM LOGO | Architectural Services Invoice (Milestone/Progress)
Firm Name: | Rainier Design Group |  |  | Invoice Number: | 2025-010
Address: | 2144 Harbor Lane, Riverton, OR 97401 |  |  | Date Issued: | 2025-05-15
Phone / Email: | (206) 555-0188 ¦ contact@rainierdesign.com |  |  | Payment Due Date: | 2025-06-14
License Number: | OR License #78942 |  |  | Project Number / Code: | MAD-APT-25
FOR
Client Name: | Horizon Builders, Inc.
Client Company: | Alexandra Mattson
Project Name: | Madison Street Apartments
Project Address: | 812 E. Parkside Ave, Maplewood, OR 97422
Fees
Project Phase | Total Fee | % Complete | Amount This Invoice | Balance Remaining | Notes
Schematic Design (SD) | 40000 | 100% | 40000 | 0
Design Development (DD) | 60000 | 80% | 48000 | 12000
Construction Documents (CD) | 75000 | 30% | 22500 | 52500
Construction Administration (CA) | 25000 | 0% | 0 | 25000
| 0 | 0% | 0 | 0
| 0 | 0% | 0 | 0
Subtotals Fees | 200000 | — | 110500 | 89500
Reimbursable Expenses
Description | Vendor Source |  | Amount | Notes
Permit Copies | City submittal |  | 250 | __
Printing (24x36 sheets) | __ |  | 180 | __
0
0
Subtotal Reimbursables |  |  | 430
Summary
|  |  | Percentage | Amount
Fees |  |  | — | 110500
Reimbursables |  |  | — | 430
Markup (% and amount) |  |  | 10.1% | 11160.5
Taxes (% and amount) |  |  | 0% | 0
Retainage (% and amount) |  |  | 5% | 5525
Total Due This Invoice (labor + reimbursables + markup + tax - retainage) |  |  |  | 116565.5
Payment Terms: (e.g., Net 30 days)
Accepted Payment Methods: (bank transfer, check, e-payment link)
E-payment Link:
Notes (e.g., “Final payment due upon substantial completion.”)
Explore how BQE software can automate your batch invoicing and other time-saving tools.

## How to Use This Template
Note – This is a view-only file and can't be edited. Please Create your own copy to edit this template: In the menu, click File > Make a copy
Section 1 – When to Use This Template Use this invoice for projects billed by completion of milestones or phases. Ideal for multi-stage projects where payment follows progress on design deliverables.
Section 2 – How to Complete the Fields Enter your firm and client information. Add your total fee for each phase in the first column. Update the % Complete field based on project progress. The Amount This Invoice field calculates from percentage values. Enter reimbursable expenses if applicable. Adjust tax and retainage percentages as needed.
Section 3 – Best Practices Keep all phases listed, even if incomplete. Use clear notes to describe progress (“DD Drawings Submitted 5/10”). Avoid rounding errors by using consistent percentages. Include a payment link to reduce turnaround time.

## About BQE Core
Simplify your billing process with BQE CORE. Create invoices directly from your time and expense data, customize by project phase, and send dozens of invoices at once with batch billing. Plus built-in e-payments help you get paid faster and improve cash flow. Learn more: https://www.bqe.com/core-invoicing
You didn’t start your firm to chase timesheets, juggle spreadsheets, or guess at profitability. You did it to make an impact through great design, strong leadership, and a thriving team. That’s why we built BQE CORE, the all-in-one firm management software created by architects and engineers to simplify how A&E firms run. From time tracking to billing, project management to accounting, CORE brings it all together in one intuitive platform. Join the thousands of firms using CORE to save time, increase profitability, and get back to the work that matters. Book a demo to see how CORE can help your firm run smarter. <BOOK A DEMO>