## Blank Construction Invoice
INSERT FIRM LOGO | Construction Progress Billing Invoice
Contractor:
Client Name:
Project Name:
Project Manager:
Project Address:
Project Number:
Application Number:
Contract Value:
Approved Change Orders:
Retainage:
Work Completed
Item Number | Description | Scheduled Value | Previous Completed | Current Completed | Stored Materials | Total Completed | % Complete | Balance Remaining
|  | 0 | 0 | 0 | 0 | 0 | 0% | 0
|  | 0 | 0 | 0 | 0 | 0 | 0% | 0
|  | 0 | 0 | 0 | 0 | 0 | 0% | 0
|  | 0 | 0 | 0 | 0 | 0 | 0% | 0
|  | 0 | 0 | 0 | 0 | 0 | 0% | 0
|  | 0 | 0 | 0 | 0 | 0 | 0% | 0
Subtotal Work Completed | — | 0 | 0 | 0 | 0 | 0 | — | 0
Summary
Breakdown |  |  | Amount | Notes
Original Contract
Change Orders
Revised Contract |  |  | 0
Total Completed to Date |  |  | 0
Retainage Withheld |  |  | 0
Net Amount Due |  |  | 0
Previous Payments - Input $ >>> |  |  | 0
Remaining Contract Balance |  |  | 0
Total Due This Invoice (Work Completed) |  |  | 0
Compliance Notes (optional):
Payment Terms: (e.g., "Net 30 days")
Accepted Payment Methods: (ACH, check, or secure e-payment link)
E-payment Link:
Notes: (e.g., “Invoice subject to agency review and approval.”)
Certification
(e.g.,“I certify that the costs presented are accurate, allowable, and allocable in accordance with contract terms and applicable regulations.”)
Signed: ____________________________________________________________________________________
Name/Title:
Date:
Simplify your workflow and get paid faster with BQE Core.

## Example Mid-payment Invoice
INSERT FIRM LOGO | Construction Progress Billing Invoice
Contractor: | Evergreen Construction Services
Client Name: | Rainier Medical Partners
Project Name: | Rainier Medical Office Expansion
Project Manager:
Project Address:
Project Number:
Application Number: | 07
Contract Value: | 2400000
Approved Change Orders: | 180000
Retainage: | 10%
Work Completed
Item Number | Description | Scheduled Value | Previous Completed | Current Completed | Stored Materials | Total Completed | % Complete | Balance Remaining
01 | Site Work | 180000 | 180000 | 0 | 0 | 180000 | 100% | 0
02 | Concrete & Foundations | 420000 | 350000 | 50000 | 0 | 400000 | 95.24% | 20000
03 | Structural Steel | 600000 | 280000 | 120000 | 40000 | 440000 | 73.33% | 160000
04 | Exterior Envelope | 520000 | 120000 | 140000 | 25000 | 285000 | 54.81% | 235000
05 | Interior Buildout | 600000 | 80000 | 95000 | 20000 | 195000 | 32.5% | 405000
06 | MEP Systems | 260000 | 30000 | 50000 | 10000 | 90000 | 34.62% | 170000
Subtotal Work Completed | — | 2580000 | 1040000 | 455000 | 95000 | 1590000 | — | 990000
Summary
Breakdown |  |  | Amount | Notes
Original Contract |  |  | 2400000
Change Orders |  |  | 180000
Revised Contract |  |  | 2580000
Total Completed to Date |  |  | 1590000
Retainage Withheld |  |  | 159000
Net Amount Due |  |  | 1431000
Previous Payments - Input $ >>> |  |  | 1180000
Remaining Contract Balance |  |  | 990000
Total Due This Invoice (Work Completed) |  |  | 251000
Compliance Notes (optional):
Payment Terms: (e.g., "Net 30 days")
Accepted Payment Methods: (ACH, check, or secure e-payment link)
E-payment Link:
Notes: (e.g., “Invoice subject to agency review and approval.”)
Certification
(e.g.,“I certify that the costs presented are accurate, allowable, and allocable in accordance with contract terms and applicable regulations.”)
Signed: ____________________________________________________________________________________
Name/Title:
Date:
Simplify your workflow and get paid faster with BQE Core.

## Example Final-payment Invoice
INSERT FIRM LOGO | Construction Progress Billing Invoice
Contractor: | Evergreen Construction Services
Client Name: | Rainier Medical Partners
Project Name: | Rainier Medical Office Expansion
Project Manager:
Project Address:
Project Number:
Application Number: | 07
Contract Value: | 2400000
Approved Change Orders: | 180000
Retainage: | 10%
Work Completed
Item Number | Description | Scheduled Value | Previous Completed | Current Completed | Stored Materials | Total Completed | % Complete | Balance Remaining
01 | Site Work | 180000 | 180000 | 0 | 0 | 180000 | 100% | 0
02 | Concrete & Foundations | 420000 | 400000 | 20000 | 0 | 420000 | 100% | 0
03 | Structural Steel | 600000 | 400000 | 160000 | 40000 | 600000 | 100% | 0
04 | Exterior Envelope | 520000 | 400000 | 95000 | 25000 | 520000 | 100% | 0
05 | Interior Buildout | 600000 | 175000 | 405000 | 20000 | 600000 | 100% | 0
06 | MEP Systems | 260000 | 80000 | 170000 | 10000 | 260000 | 100% | 0
Subtotal Work Completed | — | 2580000 | 1635000 | 850000 | 95000 | 2580000 | — | 0
Summary
Breakdown |  |  | Amount | Notes
Original Contract |  |  | 2400000
Change Orders |  |  | 180000
Revised Contract |  |  | 2580000
Total Completed to Date |  |  | 2580000
Retainage Released |  |  | 258000
Net Amount Due |  |  | 2322000
Previous Payments - Input $ >>> |  |  | 2122000
Remaining Contract Balance |  |  | 0
Total Due This Invoice (Work Completed) |  |  | 458000
Compliance Notes (optional):
Payment Terms: (e.g., "Net 30 days")
Accepted Payment Methods: (ACH, check, or secure e-payment link)
E-payment Link:
Notes: (e.g., “Invoice subject to agency review and approval.”)
Certification
(e.g.,“I certify that the costs presented are accurate, allowable, and allocable in accordance with contract terms and applicable regulations.”)
Signed: ____________________________________________________________________________________
Name/Title:
Date:
Simplify your workflow and get paid faster with BQE Core.

## Instructions
What construction progress billing is. Construction progress billing is a method of invoicing clients based on work completed to date instead of waiting until the end of the project. Contractors bill incrementally as phases of work are completed throughout the project lifecycle.
How retainage works. Retainage is a percentage of each invoice withheld by the client until substantial completion or final project closeout. It helps protect the owner by ensuring work is completed according to contract requirements.
Difference between completed work and stored materials. Completed work reflects labor and installed materials already incorporated into the project. Stored materials are materials purchased and stored on-site or approved storage locations that have not yet been installed but may still be billable.
How previous billings affect current payment due. Previous billings must be subtracted from total earned revenue to avoid double billing. The current payment due only reflects newly completed work since the last billing period.
Why percentage complete matters Percentage complete determines how much revenue has been earned for each line item or phase of work. Accurate percentages help ensure invoices reflect actual project progress and prevent overbilling or underbilling.

## About BQE Core
In BQE CORE, you can automate public works billing with full compliance tracking. CORE calculates labor, overhead, and fees based on contract rules, maintains audit trails, and generates agency-ready invoices. Learn more: https://www.bqe.com/core-invoicing