## Blank Invoice
INSERT FIRM LOGO | Engineering Progress Billing Invoice
Firm Name: | [6 empty] | Invoice Number:
Address: | [6 empty] | Date Issued:
Phone / Email: | [6 empty] | Payment Due Date:
License Number (optional): | [6 empty] | Project ID / Contract Number:
FOR
Client Name:
Company (optional):
Project Name:
Project Address:
Contract #:
Billing Progress
Description of Work (e.g., "Preliminary Design, Field Work, Construction Support, Subconsultant Services") | Original Value | % Complete (Current) | % Complete (Prior) | Earned This Period | Retainage (%) | Current Due | Cumulative Due | Notes
| 0 | 0% | 0% | 0 | 0% | 0 | 0
| 0 | 0% | 0% | 0 | 0% | 0 | 0
| 0 | 0% | 0% | 0 | 0% | 0 | 0
| 0 | 0% | 0% | 0 | 0% | 0 | 0
| 0 | 0% | 0% | 0 | 0% | 0 | 0
| 0 | 0% | 0% | 0 | 0% | 0 | 0
Subtotal Billing Progress | 0 |  |  | 0 |  | 0 | 0
Summary
Breakdown |  |  |  |  | Amount | Notes
Current Billing |  |  |  |  | 0
Previous Billings - Input Amount >>> |  |  |  |  | 0
Retainage Held to Date - Input Amount >>> |  |  |  |  | 0
Total Billed to Date |  |  |  |  | 0
Balance to Finish |  |  |  |  | 0
Total Due This Invoice (unit work + reimbursables/disbursements) |  |  |  |  | 0
Payment Terms: (e.g., "Net 30 days")
Accepted Payment Methods: (ACH, check, or secure e-payment link)
E-payment Link:
Notes: (e.g., “Progress billing based on approved Schedule of Values through [date].”)
Simplify your workflow and get paid faster with BQE Core.

## Sample Invoice
INSERT FIRM LOGO | Engineering Progress Billing Invoice
Firm Name: | Evergreen Civil Engineering | [5 empty] | Invoice Number: | 2025-078
Address: | 4421 Rainier Ave S, Seattle, WA 98118 | [5 empty] | Date Issued: | September 1, 2025
Phone / Email: | (206) 555-0475 ¦ billing@evergreence.com | [5 empty] | Payment Due Date: | September 30, 2025
License Number (optional): | WA License #57431 | [5 empty] | Project ID / Contract Number: | RDM-WM-25
FOR
Client Name: | Hilda Wilson
Company (optional): | City of Redmond Public Works
Project Name: | Downtown Water Main Replacement
Project Address: | 9902 Leary Way NE, Redmond, WA 98052
Contract #:
Billing Progress
Description of Work (e.g., "Preliminary Design, Field Work, Construction Support, Subconsultant Services") | Original Value | % Complete (Current) | % Complete (Prior) | Earned This Period | Retainage (%) | Current Due | Cumulative Due | Notes
Preliminary Design | 20000 | 100% | 100% | 0 | 5% | 0 | 19000 | Completed June
Field Surveying | 15000 | 80% | 50% | 4500 | 5% | 4275 | 11400 | Approved 8/28
Construction Support | 25000 | 40% | 20% | 5000 | 5% | 4750 | 9500 | In progress
Subconsultant Services | 10000 | 60% | 40% | 2000 | 5% | 1900 | 5700 | Invoice attached
| 0 | 0% | 0% | 0 | 0% | 0 | 0
| 0 | 0% | 0% | 0 | 0% | 0 | 0
Subtotal Billing Progress | 70000 |  |  | 11500 |  | 10925 | 45600
Summary
Breakdown |  |  |  |  | Amount | Notes
Current Billing |  |  |  |  | 10925
Previous Billings - Input Amount >>> |  |  |  |  | 25000
Retainage Held to Date - Input Amount >>> |  |  |  |  | 2400
Total Billed to Date |  |  |  |  | 35925
Balance to Finish |  |  |  |  | 34075
Total Due This Invoice (unit work + reimbursables/disbursements) |  |  |  |  | 10925
Payment Terms: (e.g., "Net 30 days") |  |  |  |  | Net 30 days
Accepted Payment Methods: (ACH, check, or secure e-payment link)
E-payment Link:
Notes: (e.g., “Progress billing based on approved Schedule of Values through [date].”) |  |  |  |  | Progress verified through client inspector on August 30, 2025.
Simplify your workflow and get paid faster with BQE Core.

## How to Use This Template
Section 1 – When to Use This Template Use this invoice when billing by progress or completion percentage rather than hourly or unit rate. Ideal for ongoing contracts with retainage.
Section 2 – How to Complete the Fields Enter firm and client details. List each work phase with its contract value. Update prior and current completion percentages. The sheet will calculate earned, retainage, and total automatically.
Section 3 – Best Practices Verify completion percentages with the client or inspector before invoicing. Include backup for subconsultant work. Always check cumulative totals for accuracy across billing periods.
Section 4 – Tips for Software Users In BQE CORE, progress billing updates automatically from your schedule of values. CORE tracks retainage, prior billings, and percent complete, then generates invoices instantly.

## About BQE Core
Automate progress billing with BQE CORE. Update your schedule of values, apply retainage, and generate progress invoices automatically. CORE tracks previous billings, calculates cumulative totals, and syncs with project KPIs to keep everything on schedule and accurate. Learn more: https://www.bqe.com/core-invoicing