## Blank Professional Serv Invoice
INSERT FIRM LOGO | Professional Services Progress Billing Invoice
Client Name:
Project Name:
Project Manager:
Project Address:
Project Number:
Contract Value:
Retainage:
Billing Period (start – end dates):
Approved Change Orders:
Invoice Number:
Invoice Date:
Work Completed
Phase | Contract Value | % Complete | Earned to Date | Previous Billed | Current Billing | Balance Remaining | Notes
| 0 | 0% | 0 | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0 | 0
Subtotal Work Completed | — | — | 0 | 0 | 0 | 0
Summary
Breakdown |  |  | Amount | Notes
Original Contract
Change Orders
Revised Contract
Total Completed to Date |  |  | 0
Retainage Withheld |  |  | 0
Previous Payments |  |  | 0
Remaining Contract Balance |  |  | 0
Total Due This Invoice (Work Completed) |  |  | 0
Compliance Notes (optional):
Payment Terms: (e.g., "Net 30 days")
Accepted Payment Methods: (ACH, check, or secure e-payment link)
E-payment Link:
Notes: (e.g., “Invoice subject to agency review and approval.”)
Certification
(e.g.,“I certify that the costs presented are accurate, allowable, and allocable in accordance with contract terms and applicable regulations.”)
Signed: ____________________________________________________________________________________
Name/Title:
Date:
Simplify your workflow and get paid faster with BQE Core.

## Example Mid-payment Invoice
INSERT FIRM LOGO | Professional Services Progress Billing Invoice
Client Name: | City of Evergreen
Project Name: | Evergreen Civic Plaza Renovation
Project Manager:
Project Address:
Project Number:
Contract Value: | 200000
Retainage: | 5%
Billing Period (start – end dates):
Approved Change Orders: | 0
Invoice Number: | PB-2048
Invoice Date: | April 1–30, 2026
Work Completed
Phase | Contract Value | % Complete | Earned to Date | Previous Billed | Current Billing | Balance Remaining | Notes
Schematic Design | 40000 | 100% | 40000 | 35000 | 5000 | 0
Design Development | 60000 | 70% | 42000 | 28000 | 14000 | 18000
Construction Documents | 55000 | 40% | 22000 | 12000 | 10000 | 33000
Construction Administration | 45000 | 10% | 4500 | 0 | 4500 | 40500
| 0 | 0% | 0 | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0 | 0
Subtotal Work Completed | — | — | 108500 | 75000 | 33500 | 91500
Summary
Breakdown |  |  | Amount | Notes
Original Contract |  |  | 200000
Change Orders |  |  | 0
Revised Contract |  |  | 200000
Total Completed to Date |  |  | 108500
Retainage Withheld |  |  | 1675
Previous Payments |  |  | 75000
Remaining Contract Balance |  |  | 91500
Total Due This Invoice (Work Completed) |  |  | 31825
Compliance Notes (optional):
Payment Terms: (e.g., "Net 30 days")
Accepted Payment Methods: (ACH, check, or secure e-payment link)
E-payment Link:
Notes: (e.g., “Invoice subject to agency review and approval.”)
Certification
(e.g.,“I certify that the costs presented are accurate, allowable, and allocable in accordance with contract terms and applicable regulations.”)
Signed: ____________________________________________________________________________________
Name/Title:
Date:
Simplify your workflow and get paid faster with BQE Core.

## Example Final-payment Invoice
INSERT FIRM LOGO | Professional Services Progress Billing Invoice
Client Name: | City of Evergreen
Project Name: | Evergreen Civic Plaza Renovation
Project Manager:
Project Address:
Project Number:
Contract Value: | 200000
Retainage: | 5%
Billing Period (start – end dates):
Approved Change Orders: | 0
Invoice Number: | PB-2099
Invoice Date: | August 1–30, 2026
Work Completed
Phase | Contract Value | % Complete | Earned to Date | Previous Billed | Current Billing | Balance Remaining | Notes
Schematic Design | 40000 | 100% | 40000 | 40000 | 0 | 0
Design Development | 60000 | 100% | 60000 | 28000 | 32000 | 0
Construction Documents | 55000 | 100% | 55000 | 12000 | 43000 | 0
Construction Administration | 45000 | 100% | 45000 | 0 | 45000 | 0
| 0 | 0% | 0 | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0 | 0
Subtotal Work Completed | — | — | 200000 | 80000 | 120000 | 0
Summary
Breakdown |  |  | Amount | Notes
Original Contract |  |  | 200000
Change Orders |  |  | 0
Revised Contract |  |  | 200000
Total Completed to Date |  |  | 200000
Retainage Released |  |  | 10000
Previous Payments |  |  | 80000
Remaining Contract Balance |  |  | 0
Total Due This Invoice (Work Completed) |  |  | 210000
Compliance Notes (optional):
Payment Terms: (e.g., "Net 30 days")
Accepted Payment Methods: (ACH, check, or secure e-payment link)
E-payment Link:
Notes: (e.g., “Invoice subject to agency review and approval.”)
Certification
(e.g.,“I certify that the costs presented are accurate, allowable, and allocable in accordance with contract terms and applicable regulations.”)
Signed: ____________________________________________________________________________________
Name/Title:
Date:
Simplify your workflow and get paid faster with BQE Core.

## Instructions
Template Purpose A professional services progress billing invoice template for architecture, engineering, consulting, and project-based firms billing by percentage complete or earned value over time.
How retainage works. Retainage is a percentage of each invoice withheld by the client until substantial completion or final project closeout. It helps protect the owner by ensuring work is completed according to contract requirements.
How previous billings affect current payment due. Previous billings must be subtracted from total earned revenue to avoid double billing. The current payment due only reflects newly completed work since the last billing period.
Why percentage complete matters Percentage complete determines how much revenue has been earned for each line item or phase of work. Accurate percentages help ensure invoices reflect actual project progress and prevent overbilling or underbilling.

## About BQE Core
In BQE CORE, you can automate public works billing with full compliance tracking. CORE calculates labor, overhead, and fees based on contract rules, maintains audit trails, and generates agency-ready invoices. Learn more: https://www.bqe.com/core-invoicing