## Blank Progress Billing Schedule
INSERT FIRM LOGO | Progress Billing Schedule
Client Name:
Project Name:
Project Manager:
Project Address:
Project Number:
Contract Value:
Retainage:
Billing Frequency:
Start Date:
Estimated Completion:
Billing Schedule
Billing Period | Phase | Planned % This Period | Cumulative % | Invoice Amount | Retainage | Net Collection | Invoice Date | Expected Payment
|  | 0% | 0% | 0 | 0 | 0
|  | 0% | 0% | 0 | 0 | 0
|  | 0% | 0% | 0 | 0 | 0
|  | 0% | 0% | 0 | 0 | 0
Subtotal Billing Schedule | — | — | — | 0 | 0 | 0 | — | —
Summary
Breakdown |  |  | Amount | Notes
Total Scheduled Billings |  |  | 0
Remaining Contract Balance |  |  | 0
Simplify your workflow and get paid faster with BQE Core.

## Example Professional Services
INSERT FIRM LOGO | Progress Billing Schedule
Client Name: | City of Evergreen
Project Name: | Evergreen Transit Corridor Study
Project Manager:
Project Address:
Project Number: | 33294
Contract Value: | 200000
Retainage: | 0%
Billing Frequency: | Monthly
Start Date: | January 2026
Estimated Completion: | September 2026
Billing Schedule
Billing Period | Phase | Planned % This Period | Cumulative % | Invoice Amount | Retainage | Net Collection | Invoice Date | Expected Payment
January | Existing Conditions | 10% | 10% | 20000 | 0 | 20000 | 2026-01-30 | 2026-02-15
February | Traffic Analysis | 15% | 25% | 30000 | 0 | 30000 | 2026-02-28 | 2026-03-15
March | Public Outreach | 12% | 37% | 24000 | 0 | 24000 | 2026-03-31 | 2026-04-15
April | Draft Recommendations | 18% | 55% | 36000 | 0 | 36000 | 2026-04-30 | 2026-05-15
Subtotal Billing Schedule | — | — | — | 110000 | 0 | 110000 | — | —
Summary
Breakdown |  |  | Amount | Notes
Total Scheduled Billings Through April |  |  | 110000
Remaining Contract Balance After April |  |  | 90000
Simplify your workflow and get paid faster with BQE Core.

## Example Commercial Construction
INSERT FIRM LOGO | Progress Billing Schedule
Client Name: | Harbor Point Development LLC
Project Name: | Harbor Point Office Complex
Project Manager:
Project Address:
Project Number: | HP-26-114
Contract Value: | 4500000
Retainage: | 5%
Billing Frequency: | Monthly
Start Date: | 2026-02-01
Estimated Completion: | 2027-02-15
Billing Schedule
Billing Period | Phase | Planned % This Period | Cumulative % | Invoice Amount | Retainage | Net Collection | Invoice Date | Expected Payment
February 2026 | Site Prep | 5% | 5% | 225000 | 11250 | 213750 | 2026-02-28 | 2026-03-15
March 2026 | Foundations | 7% | 12% | 315000 | 15750 | 299250 | 2026-03-31 | 2026-04-15
April 2026 | Structural Steel | 11% | 23% | 495000 | 24750 | 470250 | 2026-04-30 | 2026-05-15
May 2026 | Building Envelope | 12% | 35% | 540000 | 27000 | 513000 | 2026-05-31 | 2026-06-15
Subtotal Billing Schedule | — | — | — | 1575000 | 78750 | 1496250 | — | —
Summary
Breakdown |  |  | Amount | Notes
Total Scheduled Billings After May |  |  | 1575000
Remaining Contract Balance After May |  |  | 2925000
Simplify your workflow and get paid faster with BQE Core.

## Instructions
What a progress billing schedule is. A progress billing schedule is a planning and forecasting tool used to map out when invoices will be issued and when payments are expected throughout a project. Instead of showing completed work like an invoice does, the schedule helps teams estimate future billing activity based on planned project progress over time. Most progress billing schedules include projected completion percentages, estimated invoice amounts, retainage, expected payment dates, and cumulative billings. Project managers and accounting teams use the schedule to improve cash flow planning, coordinate billing expectations with clients, and monitor how billing aligns with the overall project timeline.
Difference between a billing schedule and an invoice A billing schedule is a forecast. An invoice is an actual request for payment. The billing schedule outlines planned future billings across the project lifecycle, including estimated invoice timing and projected payment amounts. It helps teams plan ahead and communicate expectations before work is completed. An invoice, by contrast, reflects actual completed work during a specific billing period. It includes finalized amounts due, percentage complete calculations, previous billings, retainage, and payment terms.
How retainage affects projected cash flow Retainage reduces the amount of cash collected during each billing cycle because a percentage of every invoice is withheld until later in the project, often until substantial completion or final closeout. For example, if a project invoice totals $100,000 and the retainage rate is 5%, the client withholds $5,000 and pays $95,000. While the full $100,000 may count toward earned revenue, only the net collected amount improves short-term cash flow. Because of this, progress billing schedules should track both projected invoice amounts and projected net collections after retainage. This gives firms a more realistic picture of expected cash flow throughout the project.
How to update percentage complete over time Percentage complete should be updated regularly as work progresses throughout the project. Most firms update progress percentages during each billing cycle, often monthly. Progress can be measured using several methods: -Labor hours completed versus estimated hours -Costs incurred versus estimated costs -Units completed -Deliverables or phases completed As percentages change, projected invoice amounts, cumulative billings, remaining contract balance, and projected cash collections should update automatically within the billing schedule. Consistent updates help keep billing aligned with actual project performance and reduce the risk of overbilling, underbilling, or delayed invoices.

## About BQE Core
In BQE CORE, you can automate public works billing with full compliance tracking. CORE calculates labor, overhead, and fees based on contract rules, maintains audit trails, and generates agency-ready invoices. Learn more: https://www.bqe.com/core-invoicing