## Blank Invoice
INSERT FIRM LOGO | Retainage Retention Engineering Invoice
Firm Name: |  |  |  | Invoice Number:
Address: |  |  |  | Date Issued:
Phone / Email: |  |  |  | Payment Due Date:
License Number (optional): |  |  |  | Project ID / Contract Number:
Billing Period (start – end dates):
FOR
Client Name:
Company (optional):
Project Name:
Project Address:
Contract #:
Billing Progress
Description (e.g., "Engineering Design Phase, Permitting & Approvals, Construction Administration") | Scheduled Value | Work Completed to Date (%) | Earned to Date | Previously Billed | Current Billing | Notes
| 0 | 0% | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0
| 0 | 0% | 0 | 0 | 0
Subtotal Total Current Billing | 0 | — | 0 | 0 | 0
Summary
Breakdown |  |  | Percentage | Amount | Notes
Total Current Billing |  |  | — | 0
Retainage Amount Input % >>> |  |  | 0% | 0
Less Retainage Net Due |  |  | — | 0
Tax (optional) Input % >>> |  |  | 0% | 0
Total Due This Invoice (total current billing - retainage) |  |  |  | 0
Retainage Released This Invoice: (Only used near project completion) |  |  | 0
Compliance Notes (optional):
Payment Terms: (e.g., "Net 30 days")
Accepted Payment Methods: (ACH, check, or secure e-payment link)
E-payment Link:
Notes: (e.g., “Retainage will be released upon project completion and client approval.”)
Simplify your workflow and get paid faster with BQE Core.

## Sample Invoice
INSERT FIRM LOGO | Retainage Retention Engineering Invoice
Firm Name: | Cascade Civil Engineering |  |  | Invoice Number: | 2025-078
Address: | 1450 Lake Union Dr, Seattle, WA 98109 |  |  | Date Issued: | 2025-08-01
Phone / Email: | (206) 555-0192 ¦ billing@cascadecivil.com |  |  | Payment Due Date: | 2025-08-31
License Number (optional): | WA License #CE-55421 |  |  | Project ID / Contract Number: | GLB-ENG-25
|  |  |  | Billing Period (start – end dates): | July 1 – July 31, 2025
FOR
Client Name: | Olivia Carter
Company (optional): | City of Seattle – Capital Projects
Project Name: | Green Lake Pedestrian Bridge
Project Address:
Contract #: | GLB-2025-08
Billing Progress
Description (e.g., "Engineering Design Phase, Permitting & Approvals, Construction Administration") | Scheduled Value | Work Completed to Date (%) | Earned to Date | Previously Billed | Current Billing | Notes
Design Phase | 50000 | 100% | 50000 | 45000 | 5000
Permitting | 30000 | 80% | 24000 | 18000 | 6000
Construction Admin | 40000 | 50% | 20000 | 10000 | 10000
| 0 | 0% | 0 | 0 | 0
Subtotal Total Current Billing | 120000 | — | 94000 | 73000 | 21000
Summary
Breakdown |  |  | Percentage | Amount | Notes
Total Current Billing |  |  | — | 21000
Retainage Amount Input % >>> |  |  | 10% | 2100 | Total Retainage Held to Date: $9,400
Less Retainage Net Due |  |  | — | 18900
Tax (optional) Input % >>> |  |  | 0% | 0
Total Due This Invoice (total current billing - retainage) |  |  |  | 18900
Retainage Released This Invoice: (Only used near project completion) |  |  | 0
Compliance Notes (optional): |  |  | Invoice prepared in accordance with applicable contract terms and industry guidelines (e.g., FAR, DCAA, ACEC). Supporting documentation available upon request.
Payment Terms: (e.g., "Net 30 days") |  |  | Net 30 days
Accepted Payment Methods: (ACH, check, or secure e-payment link)
E-payment Link:
Notes: (e.g., “Retainage will be released upon project completion and client approval.”) |  |  | Retainage held at 10% per contract terms.
Simplify your workflow and get paid faster with BQE Core.

## How to Use This Template
Section 1 – When to Use This Template Use for projects with retainage requirements, especially construction or public works contracts where a portion of payment is withheld until completion.
Section 2 – How to Complete the Fields Enter firm, client, and project details. Fill in scheduled values and percent complete for each phase. Confirm previously billed amounts. Apply retainage percentage per contract terms.
Section 3 – Best Practices Align retainage percentage exactly with contract language. Track cumulative retainage carefully across invoices. Clearly indicate retainage release in final billing.
Section 4 – Tips for Software Users In BQE CORE, you can automate progress billing and retainage tracking. CORE calculates earned revenue, applies retainage rules, and tracks withheld balances until final release—reducing manual errors and improving cash flow visibility.

## About BQE Core
Automate progress billing and retainage tracking with BQE CORE. Calculate earned revenue, apply retainage automatically, and track withheld balances across the life of your project all in one place. Learn more: https://www.bqe.com/core-invoicing